## Kick-off
Venues: Austin, Nashville, RWS, Seattle & Kitchener | Key: |  | Event Date | [7 empty] | OGT Milestone | [7 empty] | WW Milestone | [6 empty] | Meetings
Date: August 5th 2026
Client: Oracle Global Tech Program
|  | Week 1 |  |  | 2026-05-11 |  | Week 2 |  |  | 2026-05-18 |  | Week 3 |  |  | 2026-05-25 |  | Week 4 |  |  | 2026-06-08 |  | Week 5 |  |  | 2026-06-15 |  | Week 6 |  |  | 2026-06-22 |  | Week 7 |  |  | 2026-06-29 |  | Week 8 |  |  | 2026-07-06 |  | Week 9 |  |  | 2026-07-13 |  | Week 10 |  |  | 2026-07-20 |  | Week 11 |  |  | 2026-07-27 |  | Week 12 |  |  | 2026-08-03 |  | Week 13 |  |  | 2026-08-10 |  | Week 14 |  |  | 2026-08-17
Timeline |  | M | T | W | Th | F | M | T | W |  | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Who
CLIENT/ WHITEWALL MEETINGS
Kick Off Meeting
Client Meeting | bar: Week 4 W; Week 6 W; Week 7 W; Week 8 W; Week 9 W; Week 10 W; Week 11 W
Internal 24 hour meeting | bar: Week 12 M
Client Show and Tell | bar: 2026-07-27 F
Post-event Debrief | bar: Week 14 W
REGISTRATION & GUEST MANAGEMENT
Initial Attendee List sent to Whitewall
Badge design for 1st review | bar: Week 5 M
Badge design - client feedback | bar: 2026-06-15 F
Badge design finalized | bar: Week 6 M
Registration Equipment Booked | bar: Week 8 M
Ambassadors Booked | bar: Week 8 M
Ambassadors Briefing | bar: Week 11 W
VENUE / CATERING / TRANSPORT
External Venues Confirmed (TBC)
Floorplan/ Room Allocations Confirmed | bar: Week 3 M
Numbers for delegates confirmed | bar: Week 3 M
BEO 1st draft to venue (external venues) | bar: 2026-05-25 F
BEO Meeting (external venues) | bar: 2026-06-08 F
Final catering numbers | bar: 2026-07-13 F
GENERAL OPERATIONS/TECHNICAL
Tech Eqpt discussed (Internal & External) | bar: Week 3 M
Tech Eqpt finalized | bar: 2026-06-08 F
Tech Mgrs Confirmed | bar: Week 6 M; Week 11 M
Plans & layouts drafted and discussed | bar: Week 6 M
Plans and layouts finalized | bar: 2026-06-29 F
Technical Managers Briefing | bar: Week 11 T
CURRICULUM/FACILITATORS/VOLUNTEERING
Content provided to WW
Content Design for Client Review | bar: F
Client Feedback on Content | bar: Week 3 M
Activations Finalized | bar: 2026-05-25 F
Volunteering Activities Finalized | bar: 2026-06-08 F
Volunteering Materials Ordered | bar: Week 5 M
1st draft of designed content provided for review | bar: Week 6 M
1st draft of printed materials provided | bar: Week 6 M
Client review deadline | bar: 2026-06-22 F
Local Charities identified as beneficiaries (if required) | bar: 2026-07-06 F
2nd draft of designed content provided for review | bar: Week 8 M
2nd draft of printed materials provided | bar: Week 8 M
Content Finalized | bar: Week 9 M
Print Deadline | bar: 2026-07-20 F
Delivery Date | bar: Week 12 T
CONTENT
Faciltators confirmed | bar: Week 3 M
Faciltator Briefing | bar: Week 5 M
Content and Speakers Finalized | bar: Week 6 M
Props & Scenic requirements confirmed | bar: 2026-06-22 F
Props & Scenic ordered | bar: Week 7 M
Headshot and Photobooths ordered | bar: Week 8 M
Props & Scenic delivered | bar: Week 12 T
Facilitator - Train the Trainer Day (TBC from OGT) | bar: Week 9 M; Week 10 W
Speakers / Presenters Rehearsal - onsite | bar: Week 12 T
SWAG/WELCOME KIT/GUEST APP/PARTICIPANT KITS
Swag options shared with client for review | bar: Week 4 W
Client feedback on items | bar: Week 5 W
Client Signoff on items | bar: 2026-06-15 F
Swag Items ordered | bar: Week 8 M
Items delivered | bar: Week 12 T
WEBSITE/SURVEY TOOL
Website Design Brief | bar: Week 7 M
Website Creation | bar: Week 7 T to 2026-07-06 Th
Client Review/Approval (By email) | bar: 2026-07-06 F
Survey Client Brief | bar: Week 9 M
Survey Client Design | bar: Week 9 T to 2026-07-13 F
Client Review/Approval (By email) | bar: Week 10 M
Questions Finalized | bar: 2026-07-20 F
Asset Delivery | bar: Week 11 M
Delivery of Data | bar: 2026-08-03 F
BRANDING/DESIGN WORK
Creative Briefing | bar: Week 6 M
Creation | bar: Week 8 M to 2026-07-13 Th
Client Review/Approval (By email) | bar: 2026-07-13 F
Final edits | bar: Week 10 M to 2026-07-20 Th
Asset Delivery | bar: 2026-07-20 F
VLOG
Creative Briefing | bar: Week 7 M
Pre-work design | bar: Week 7 T to 2026-06-29 F
Client Review | bar: Week 8 M
60 Second Sizzle Reel
Sizzle Reel Briefing | bar: Week 10 M to Week 10 W
Creation | bar: Week 13 M to Week 13 W
Client Review/Approval (By email) | bar: 2026-08-10 Th to 2026-08-10 F
Final edits | bar: Week 14 M to Week 14 T
Asset Delivery | bar: Week 14 W
30 Second Sizzle Reel
Sizzle Reel Briefing | bar: Week 10 M to Week 10 W
Creation | bar: Week 13 W to 2026-08-10 F
Client Review/Approval (By email) | bar: Week 14 M to Week 14 T
Final edits | bar: Week 14 W
Asset Delivery | bar: Week 14 W

## Initialize
Project: Oracle Global Tech FY27 - //Initialize
Venue: TBC | Key: |  | Event Date | [7 empty] | OGT Milestone | [7 empty] | WW Milestone | [6 empty] | Meetings
Date: October 13th -15th 2026
Client: Oracle `Global Tech Program
|  | Week 1 |  |  | 2026-07-27 |  | Week 2 |  |  | 2026-08-03 |  | Week 3 |  |  | 2026-08-10 |  | Week 4 |  |  | 2026-08-17 |  | Week 5 |  |  | 2026-08-24 |  | Week 6 |  |  | 2026-08-31 |  | Week 7 |  |  | 2026-09-07 |  | Week 8 |  |  | 2026-09-14 |  | Week 9 |  |  | 2026-09-21 |  | Week 10 |  |  | 2026-09-28 |  | Week 11 |  |  | 2026-10-05 |  | Week 12 |  |  | 2026-10-12 |  | Week 13 |  |  | 2026-10-19 |  | Week 14 |  |  | 2026-10-26
Timeline |  | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Who
CLIENT/ WHITEWALL MEETINGS
Kick Off Meeting | bar: Week 1 W
Client Meeting | bar: Week 2 W; Week 4 W; Week 6 W; Week 7 W; Week 8 W; Week 9 W; Week 10 W; Week 11 W
Internal 24 hour meeting | bar: Week 12 M
Client Show and Tell | bar: 2026-10-05 F
Post-event Debrief | bar: Week 14 W
REGISTRATION & GUEST MANAGEMENT
Initial Attendee List sent to Whitewall | bar: Week 2 M
Badge design for 1st review | bar: Week 5 M
Badge design - client feedback | bar: 2026-08-24 F
Badge design finalized | bar: Week 6 M
Registration Equipment Booked | bar: Week 8 M
Ambassadors Booked | bar: Week 8 M
Ambassadors Briefing | bar: Week 11 W
VENUE / ACCOMODATION / CATERING / TRANSPORT
Floorplan/ Room Allocations Confirmed | bar: Week 3 M
Numbers for delegates confirmed | bar: Week 3 M
BEO 1st draft to venue | bar: 2026-08-10 F
BEO Meeting | bar: 2026-08-17 F
Transfer lists provided to Whitewall | bar: 2026-08-24 F
Airport Transfers booked | bar: Week 6 M
Hotel Booking link provided to OGT for distribution | bar: Week 6 T
Final catering numbers | bar: 2026-09-21 F
GENERAL OPERATIONS/TECHNICAL
Tech Eqpt discussed | bar: Week 3 M
Tech Eqpt finalized | bar: 2026-08-17 F
Tech Mgr Confirmed | bar: Week 6 M; Week 11 M
Plans & layouts drafted and discussed | bar: Week 6 M
Plans and layouts finalized | bar: 2026-09-07 F
Technical Manager Briefing | bar: Week 11 T
CURRICULUM/FACILITATORS/VOLUNTEERING
Content provided to WW | bar: Week 2 M
Content Design for Client Review | bar: 2026-08-03 F
Client Feedback on Content | bar: Week 3 M
Activations Finalized | bar: 2026-08-10 F
Volunteering Activities Finalized | bar: 2026-08-17 F
Volunteering Materials Ordered | bar: Week 5 M
1st draft of designed content provided for review | bar: Week 6 M
1st draft of printed materials provided | bar: Week 6 M
Client review deadline | bar: 2026-08-31 F
Local Charities identified as beneficiaries (if required) | bar: 2026-09-14 F
2nd draft of designed content provided for review | bar: Week 8 M
2nd draft of printed materials provided | bar: Week 8 M
Content Finalized | bar: Week 9 M
Print Deadline | bar: 2026-09-28 F
Delivery Date | bar: Week 12 T
CONTENT
Faciltators confirmed | bar: Week 3 M
Faciltator Briefing | bar: Week 5 M
Content and Speakers Finalized | bar: Week 6 M
Props & Scenic requirements confirmed | bar: 2026-08-31 F
Props & Scenic ordered | bar: Week 7 M
Headshot and Photobooths ordered | bar: Week 8 M
Props & Scenic delivered | bar: Week 12 T
Facilitator - Train the Trainer Day (TBC from OGT) | bar: Week 9 M
Speaker Rehearsals - online | bar: Week 11 M
Speakers / Presenters Rehearsal - onsite | bar: Week 12 T
SWAG/WELCOME KIT/GUEST APP/PARTICIPANT KITS
Welcome Kit Options Shared with client for review | bar: Week 3 W
Swag options shared with client for review | bar: Week 4 W
Client feedback on items | bar: Week 5 W
Client Signoff on items | bar: 2026-08-24 F
Swag Items ordered | bar: Week 8 M
Welcome Kit items ordered | bar: Week 8 M
Items delivered | bar: Week 12 T
EVENING RECEPTIONS
Travellers Reception Content, Menu and Design to Client | bar: Week 6 M
Eveming Reception Content, Menu and Design to Client | bar: Week 7 M
Client sign off on Travellers Reception | bar: 2026-08-31 F
Client sign off on Evening Reception | bar: 2026-09-07 F
Traveller Reception Finalized | bar: 2026-09-21 F
Evening Reception Finalized | bar: 2026-09-21 F
WEBSITE/SURVEY TOOL
Website Design Brief | In Kick-Off Timeline
Website Creation | In Kick-Off Timeline
Client Review/Approval (By email) | In Kick-Off Timeline
Survey Client Brief | In Kick-Off Timeline
Survey Client Design | In Kick-Off Timeline
Client Review/Approval (By email) | In Kick-Off Timeline
Questions Finalized | bar: 2026-09-28 F
Asset Delivery | bar: Week 11 M
Delivery of Data | bar: 2026-10-12 F
BRANDING/DESIGN WORK
Creative Briefing | bar: Week 6 M
Creation | bar: Week 8 M to 2026-09-21 Th
Client Review/Approval (By email) | bar: 2026-09-21 F
Final edits | bar: Week 10 M to 2026-09-28 Th
Asset Delivery | bar: 2026-09-28 F
VLOG
Creative Briefing | bar: Week 7 M
Pre-work design | bar: Week 7 T to 2026-09-07 F
Client Review | bar: Week 8 M
60 Second Sizzle Reel
Sizzle Reel Briefing | bar: Week 10 M to Week 10 W
Creation | bar: Week 13 M to Week 13 W
Client Review/Approval (By email) | bar: 2026-10-19 Th to 2026-10-19 F
Final edits | bar: Week 14 M to Week 14 T
Asset Delivery | bar: Week 14 W
30 Second Sizzle Reel
Sizzle Reel Briefing | bar: Week 10 M to Week 10 W
Creation | bar: Week 13 W to 2026-10-19 F
Client Review/Approval (By email) | bar: Week 14 M to Week 14 T
Final edits | bar: Week 14 W
Asset Delivery | bar: Week 14 W

## Optimize
Project: Oracle Global Tech FY27 - //Optimize
Venue: TBC | Key: |  | Event Date | [7 empty] | OGT Milestone | [7 empty] | WW Milestone | [6 empty] | Meetings
Date: February 16th - 18th 2026
Client: Oracle Global Tech Program
|  | Week 1 |  |  | 2026-11-30 |  | Week 2 |  |  | 2026-12-07 |  | Week 3 |  |  | 2026-12-14 |  | Week 4 |  |  | 2026-12-21 |  | Week 5 |  |  | 2026-12-28 |  | Week 6 |  |  | 2026-01-04 |  | Week 7 |  |  | 2026-01-11 |  | Week 8 |  |  | 2026-01-18 |  | Week 9 |  |  | 2026-01-25 |  | Week 10 |  |  | 2026-02-01 |  | Week 11 |  |  | 2026-02-08 |  | Week 12 |  |  | 2026-02-15 |  | Week 13 |  |  | 2026-02-22 |  | Week 14 |  |  | 2026-03-01
Timeline |  | M | T | W | Th | F | M | T | W |  | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
| Who | [9 empty] | 2026-12-21 Th: Holiday break; Week 5 M: Holiday break
CLIENT/ WHITEWALL MEETINGS
Kick Off Meeting
Client Meeting | bar: Week 4 W; Week 6 W; Week 7 W; Week 8 W; Week 9 W; Week 10 W; Week 11 W
Internal 24 hour meeting | bar: Week 12 M
Client Show and Tell | bar: 2026-02-08 F
Post-event Debrief | bar: Week 14 W
REGISTRATION & GUEST MANAGEMENT
Initial Attendee List sent to Whitewall
Badge design for 1st review | bar: Week 4 W
Badge design - client feedback | bar: Week 6 M
Badge design finalized | bar: Week 6 T
Registration Equipment Booked | bar: Week 8 M
Ambassadors Booked | bar: Week 8 M
Ambassadors Briefing | bar: Week 11 W
VENUE / ACCOMODATION / CATERING / TRANSPORT
Floorplan/ Room Allocations Confirmed | bar: Week 3 M
Numbers for delegates confirmed | bar: Week 3 M
BEO 1st draft to venue | bar: 2026-12-14 F
BEO Meeting | bar: Week 4 W
Transfer lists provided to Whitewall | bar: Week 6 M
Airport Transfers booked | bar: Week 6 T
Hotel Booking link provided to OGT for distribution | bar: Week 6 W
Final catering numbers | bar: 2026-01-25 F
GENERAL OPERATIONS/TECHNICAL
Tech Eqpt discussed | bar: Week 3 M
Tech Eqpt finalized | bar: Week 4 W
Tech Mgr Confirmed | bar: Week 6 M; Week 11 M
Plans & layouts drafted and discussed | bar: Week 6 M
Plans and layouts finalized | bar: 2026-01-11 F
Technical Manager Briefing | bar: Week 11 T
CURRICULUM/FACILITATORS/VOLUNTEERING
Content provided to WW
Content Design for Client Review | bar: F
Client Feedback on Content | bar: Week 3 M
Activations Finalized | bar: 2026-12-14 F
Volunteering Activities Finalized | bar: Week 4 W
Volunteering Materials Ordered | bar: Week 6 M
1st draft of designed content provided for review | bar: Week 6 M
1st draft of printed materials provided | bar: Week 6 M
Client review deadline | bar: 2026-01-04 F
Local Charities identified as beneficiaries (if required) | bar: 2026-01-18 F
2nd draft of designed content provided for review | bar: Week 8 M
2nd draft of printed materials provided | bar: Week 8 M
Content Finalized | bar: Week 9 M
Print Deadline | bar: 2026-02-01 F
Delivery Date | bar: Week 12 T
CONTENT
Faciltators confirmed | bar: Week 3 M
Faciltator Briefing | bar: Week 4 W
Content and Speakers Finalized | bar: Week 6 M
Props & Scenic requirements confirmed | bar: 2026-01-04 F
Props & Scenic ordered | bar: Week 7 M
Options for Guest Speaker to Client | bar: Week 4 W; Week 8 M
Client Feedback on Guest Speaker | bar: Week 6 M; Week 8 M
Guest Speaker Booked | bar: Week 6 T; Week 8 M
Headshot and Photobooths ordered | bar: Week 8 M
Props & Scenic delivered | bar: Week 12 T
Facilitator - Train the Trainer Day (TBC from OGT) | bar: Week 9 M; Week 10 W
Guest Speaker Briefing | bar: Week 11 M
Speaker Rehearsals - online | bar: Week 11 M
Speakers / Presenters Rehearsal - onsite | bar: Week 12 T
SWAG/WELCOME KIT/GUEST APP/PARTICIPANT KITS
Welcome Kit Options Shared with client for review | bar: Week 3 W
Swag options shared with client for review | bar: Week 4 W
Client feedback on items | bar: Week 6 M
Client Signoff on items | bar: Week 6 W
Swag Items ordered | bar: Week 8 M
Welcome Kit items ordered | bar: Week 8 M
Items delivered | bar: Week 12 T
EVENING RECEPTIONS
Travellers Reception Content, Menu and Design to Client | bar: Week 6 M
Eveming Reception Content, Menu and Design to Client | bar: Week 7 M
Client sign off on Travellers Reception | bar: 2026-01-04 F
Client sign off on Evening Reception | bar: 2026-01-11 F
Traveller Reception Finalized | bar: 2026-01-25 F
Evening Reception Finalized | bar: 2026-01-25 F
WEBSITE/SURVEY TOOL
Website Design Brief | In Kick-Off timeline
Website Creation | In Kick-Off timeline
Client Review/Approval (By email) | In Kick-Off timeline
Survey Client Brief | In Kick-Off timeline
Survey Client Design | In Kick-Off timeline
Client Review/Approval (By email) | In Kick-Off timeline
Questions Finalized | bar: 2026-02-01 F
Asset Delivery | bar: Week 11 M
Delivery of Data | bar: 2026-02-15 F
BRANDING/DESIGN WORK
Creative Briefing | bar: Week 6 M
Creation | bar: Week 8 M to 2026-01-25 Th
Client Review/Approval (By email) | bar: 2026-01-25 F
Final edits | bar: Week 10 M to 2026-02-01 Th
Asset Delivery | bar: 2026-02-01 F
VLOG
Creative Briefing | bar: Week 7 M
Pre-work design | bar: Week 7 T to 2026-01-11 F
Client Review | bar: Week 8 M
60 Second Sizzle Reel
Sizzle Reel Briefing | bar: Week 10 M to Week 10 W
Creation | bar: Week 13 M to Week 13 W
Client Review/Approval (By email) | bar: 2026-02-22 Th to 2026-02-22 F
Final edits | bar: Week 14 M to Week 14 T
Asset Delivery | bar: Week 14 W
30 Second Sizzle Reel
Sizzle Reel Briefing | bar: Week 10 M to Week 10 W
Creation | bar: Week 13 W to 2026-02-22 F
Client Review/Approval (By email) | bar: Week 14 M to Week 14 T
Final edits | bar: Week 14 W
Asset Delivery | bar: Week 14 W